## Feuil1
prio | next step | next big step | not for now | not decided | work in progress !
Fini
|  |  |  | Progression | Reste :
Stepchart
| Precision |  |  | 100%
|  | Display "slow/fast" |  | 100%
| Score |  |  | 100% | Caler selon la résolution - Prendre en compte le quad
| life |  |  | 100% | Fini - Caler selon la résolution
| mine |  |  | 100%
| combo |  |  | 100%
|  | Mettre combo derrière et centré |  | 100%
| combo-rush |  |  | 0%
| audio |  |  | 100%
| song progressbar |  |  | 100% | Rajouter une petite particule ?
| offset |  |  | 100%
| background change |  |  | 0%
| Bump arrow model (flash) |  |  | 100% | Façon plus opti ?
| Background scene |  |  | -% | Améliorable !
| Optimisation |  |  | En cours | Idée : SetActive les gameObject + setDisable les particules
| Display medal |  |  | 0%
| Display prec count during game |  |  | 0%
Game screens :
Splash screen
| Score screen |  |  | 0%
| Press start |  |  | 50% | Boutons faits : faire une fake stepchart à gauche + activer les boutons
| Mode screen |  |  | 0%
|  | Aventure |  | 0%
|  |  | Normal (1-13) | 0%
|  |  | Expert (9-20) | 0%
|  |  | Super Expert (9-20) | 0%
|  | Fun | 1j, 2j, mode 8t | 0%
|  | Modes |  | 0%
|  |  | Courses random | 0%
|  |  | Survival | 0%
|  |  | Zone | 0%
|  |  | Boss battle | 0%
|  | Option |  | 0%
|  |  | Key mapping | 0%
|  |  | Arrow skin select | 0%
|  |  | timing ? | 0%
|  |  | general offset | 0%
|  |  | graphics options ? | 0%
|  |  | sound option ? | 0%
| Songwheel screen |  |  | 0%
| Song option screen |  |  | 0%
|  | Light options |  | 0%
| Profiles screen |  |  | 0%
|  | Save/Load option |  | 0%
Others stuff
| Achievements |  |  | 0%
| Keyboard/dancepad mode |  |  | 0%
| Font |  |  | 50% | Necropole X selectionnée + Zekton ?
| Asset graphique |  |  | 0%
|  | Medaille |  | 0%
|  | Notes ? Autres ? |  | 0%
Managers
| AventureManager (Stepchart cryptées) |  |  | 0%
| DataManager |  |  | 0%
| SaveManager |  |  | 0%
| TextManager |  |  | 0%
| LoadChartManager |  |  | 50% | en cours
|  | Rush/Cross detection |  | 0%
Alpha test
| Alpha Test ergonomie/interface |  |  | 0%
| Alpha Test content |  |  | 0%
| Alpha Test gameplay |  |  | 0%
Beta test
| Panel joueurs experts |  |  | 0%
| Panel joueurs débutants |  |  | 0%