## Feuil1
Planning New version
Build | Categorie | SubCategorie | Title | Progression | Comments
| Asset Graphique |  | Medals | 100%
| ScoreScreen |  | Paufinage Graphique | 99% | Tester des mix pour les graph, tester le nouveau graph
200 | ScoreScreen |  | Retry / Quit | 100%
| Stepchart / ScoreScreen |  | Transistion | 100%
| Stepchart | Failed | Retry / Quit | 90% | Regarder aussi l'explosion bizarre full combo, tester, bug au niveau de la disparition
| Stepchart | Option "Display" | Incrustation | 90% | Tester
| Wheelsong | Stepchart | Transistion "splashcreen" | 5% | Tester le son
| Stepchart | Chanson qui ne marche pas |  | 100% | Tester quand même "My Name Is"
300 | MainMenu |  | Ajout 1J, LAN, 8t | 0% | Baisser le volume doucement transition
| ProfilManager |  | Creation concept | stand by | Trucs à rajouter par la suite
| ProfilManager / Wheelsong |  | Incrustation | 0%
| WHeelsong |  | Display medals | 0%
| Wheelsong |  | Display best scores | 0%
400 | ProfilManager / ScoreScreen |  | Incrustation | 0%
| General | Voix |  | 0%
500 | SplashScreen |  |  | 0%
| SplashScreen | Ecran d'init de profile |  | 0%
| SplashScreen | Load profile |  | 0%
600 | SplashScreen | Creation de profil |  | 0%
| Asset Graphique | Creation | Fleche | 0%
| Asset Graphique | Creation | boule | 0%
| Asset Graphique | Creation | Spé | 0%
700 | Asset Graphique | Stepchart | Incrustation | 0%
| Première phase de test privée |  |  | 0% | Mettre la config du globaloffset second + les touches dans un txt
| Option screen | Creation | GlobalOffset | 0%
| Option screen | Creation | Default parameters | 0%
| Option screen | Creation | Vitesse molette | 0%
| Option screen | Creation | Mode "rapide" | 0%
| Option screen | Creation | Mode tapis + raccourci keyboard | 0% | Faire en sorte que InGameScript prenne 2 touches par bind
| Option screen | Creation | Binding touches | 0%
| Option screen | Creation | Save load profile | 0%
| Option screen | Creation | Audio | 0%
| Option screen | Creation | Video ?? | 0%
800 | Mainmenu | OptionScreen | Incrustation | 0% | Corriger les bugs des mines avec
| Stepchart | Mine | Ajouter le son | 0%
| Stepchart |  | "CubeScore" (Wister idea) | 0%
| Wheelsong | dll | dll previewSong | 0%
900 | Wheelsong |  | Tri | 0%
| Wheelsong | Rate |  | 0% | Correction de la detection de cross, sons (partout), correction son wheel song
| General |  | Correction générale + optim | 0%
1000 | Première phase de test publique |  |  | 0%
| Network | Mode LAN | Creation | 0%
| Stepchart | LAN | Incrustation | 0%
| Wheelsong | LAN | Incrustation | 0%
| MainMenu | LAN | Incrustation | 0%
| Network | Recupration de profil |  | 0%
2000 | Deuxième phase de test publique |  |  | 0%
3000 | Tutorial |  |  | 0%
4000 | Modes | Courses |  | 0%
5000 | Modes | Survival |  | 0%
6000 | Modes | Zone |  | 0%
| Stepchart | Mode repeat |  | 0%
7000 | Achievements |  |  | 0%
| Mode aventure |  |  | 0%
v1 | Pack Cublast Originals |  |  | 0%
v1.1 | Mode 8t |  |  | 0%
v1.2 | Editor |  |  | 0%