## Feuil1
Planning New version
Build | Categorie | SubCategorie | Title | Progression | Comments
| Asset Graphique |  | Medals | 100%
| ScoreScreen |  | Paufinage Graphique | 100% | Signaler les morts dans le graph
200 | ScoreScreen |  | Retry / Quit | 100%
| Stepchart / ScoreScreen |  | Transistion | 100%
| Stepchart | Failed | Retry / Quit | 70% | Regarder aussi l'explosion bizarre full combo, tester
| Stepchart | Option "Display" | Incrustation | 10% | Reflechir à un truc propre
| Wheelsong |  | Transistion | 0% | Si le temps : Faire le main son de la wheel song correctement
| Stepchart | Chanson qui ne marche pas |  | 0%
300 | MainMenu |  | Ajout 1J, LAN, 8t | 0% | Baisser le volume doucement transition
| ProfilManager |  | Creation concept | 0%
| ProfilManager / Wheelsong |  | Incrustation | 0%
| WHeelsong |  | Display medals | 0%
| Wheelsong |  | Display best scores | 0%
| ProfilManager / ScoreScreen |  | Incrustation | 0%
400 | Save/Load profil |  |  | 0%
| General | Voix |  | 0%
500 | SplashScreen |  |  | 0%
600 | Creation de profil |  |  | 0%
| Asset Graphique | Creation | Fleche | 0%
| Asset Graphique | Creation | boule | 0%
| Asset Graphique | Creation | Spé | 0%
700 | Asset Graphique | Stepchart | Incrustation | 0%
| Option screen | Creation | GlobalOffset | 0%
| Option screen | Creation | Default parameters | 0%
| Option screen | Creation | Vitesse molette | 0%
| Option screen | Creation | Mode tapis + raccourci | 0%
| Option screen | Creation | Binding touches | 0%
| Option screen | Creation | Save load profile | 0%
| Option screen | Creation | Audio | 0%
| Option screen | Creation | Video ?? | 0%
800 | Mainmenu | OptionScreen | Incrustation | 0%
| Stepchart | Mine | Ajouter le son | 0% | Corriger les bugs des mines avec
| Stepchart |  | "CubeScore" (Wister idea) | 0%
| Wheelsong | dll | dll previewSong | 0%
900 | Wheelsong |  | Tri | 0%
| Wheelsong | Rate |  | 0%
1000 | General |  | Correction générale | 0% | Correction de la detection de cross, sons (partout), correction son wheel song
| Network | Mode LAN | Do it | 0%
| Stepchart | LAN | Incrustation | 0%
| Wheelsong | LAN | Incrustation
| MainMenu | LAN | Incrustation | 0%
| Network | Recupration de profil |  | 0%
2000 | Première phase de test publique |  |  | 0%
3000 | Tutorial |  |  | 0%
4000 | Modes | Courses |  | 0%
5000 | Modes | Survival |  | 0%
6000 | Modes | Zone |  | 0%
| Stepchart | Mode repeat |  | 0%
7000 | Achievements |  |  | 0%
| Mode aventure |  |  | 0%
v1 | Pack Cublast Originals |  |  | 0%
v1.1 | Mode 8t |  |  | 0%
v1.2 | Editor |  |  | 0%