## Feuil1
prio | next step | next big step | not for now | not decided | work in progress !
Fini
|  |  |  | Progression | Reste :
Stepchart
| Precision |  |  | 100%
|  | Display "slow/fast" |  | 100%
| Score |  |  | 100% | Caler selon la résolution - Prendre en compte le quad
| life |  |  | 100% | Fini - Caler selon la résolution
| mine |  |  | 100% | Ajouter le son
| combo |  |  | 100%
|  | Mettre combo derrière et centré |  | 100%
combo-rush
| audio |  |  | 100% | Changer le streaming en loading complet
| song progressbar |  |  | 100%
| offset |  |  | 100%
| background change |  |  | 0%
| Option affection |  |  | 0%
| Failed |  |  | 0%
| Bump arrow model (flash) |  |  | 100% | Façon plus opti ?
| Background scene |  |  | -% | Améliorable !
| Optimisation |  |  | En cours | Idée : Particle : Mettre un script pour les disable si !isPlaying, gameObject : Mettre un script qui a la liste de tous les GO et active ceux < à 10 sec du timer
Display medal
Display prec count during game
Game screens :
| Splash screen |  |  | 0%
| Score screen |  |  | 0%
| Press start |  |  | 100%
| Mode screen |  |  | 100%
|  | Aventure |  | 0%
|  |  | Normal (1-13) | 0%
|  |  | Expert (9-20) | 0%
|  |  | Super Expert (9-20) | 0%
|  | Fun | 1j, 2jLAN, mode 8t | 0%
|  | Modes |  | 0%
|  |  | Courses random | 0%
|  |  | Survival | 0%
|  |  | Zone | 0%
|  |  | Boss battle | 0%
|  | Tuto |  | 0%
|  |  | tuto classique | 0%
|  |  | Mode "repeat" val | 0%
|  | Option |  | 0%
|  |  | Key mapping | 0%
|  |  | Arrow skin select | 0%
|  |  | timing ? | 0%
|  |  | general offset | 0%
|  |  | graphics options ? | 0%
|  |  | sound option ? | 0%
| Songwheel screen |  |  | 90% | En stand by de l'implémentation des profils
|  | Packs |  | 100%
|  | Songs |  | 100%
|  | Description |  | 100% | Si possible de modifier ?
|  | Choix difficulté |  | 100%
|  | Display medals |  | 0% | En attente de l'implémentation des profils
|  | Display best score |  | 0% | idem
|  | Tri |  | 0%
|  | Lancement song |  | 0% | Pas compliqué
| Song option screen |  |  | 50% | FadeIn / FadeOut effectué : next step : afficher les options
|  | Light options |  | 0%
| Profiles screen |  |  | 0%
|  | Save/Load option |  | 0%
Others stuff
| Network |  |  | 0%
Update Profiles
| Achievements |  |  | 0%
| Keyboard/dancepad mode |  |  | 0%
| Font |  |  | 100% | Necropole X selectionnée + Zekton
| Asset graphique |  |  | 0%
|  | Medaille |  | 0%
|  | Skin "<" |  | 0%
|  | Skin "rond" |  | 0%
|  | Skin "flèche" |  | 0% | Tester le refresh !!!!
Managers
| AventureManager (Stepchart cryptées) |  |  | 0%
| DataManager |  |  | avec le temps
| ProfileManager |  |  | 0%
| TextManager |  |  | 100%
| FadeManager |  |  | 100% | D'autres trucs à rajouter par la suite ?
| LoadChartManager |  |  | 100% | D'autres trucs à rajouter par la suite ?
|  | Rush/Cross detection |  | 90% | Améliorer les cross detection (suite 1-2-3-1)
Alpha test
| Alpha Test ergonomie/interface |  |  | 0%
| Alpha Test content |  |  | 0%
| Alpha Test gameplay |  |  | 0%
Beta test
| Panel joueurs experts |  |  | 0%
| Panel joueurs débutants |  |  | 0%