## Feuil1
Planning New version
Build | Categorie | SubCategorie | Title | Code | Unity | Test | Comments | Date approx
| Asset Graphique |  | Medals | 100% | 100% | 100%
| ScoreScreen |  | Paufinage Graphique | 100% | 100% | 100%
200 | ScoreScreen |  | Retry / Quit | 100% | 100% | 100%
| Stepchart / ScoreScreen |  | Transistion | 100% | 100% | 100%
| Stepchart | Failed | Retry / Quit | 100% | 100% | 100%
| Stepchart | Option "Display" | Incrustation | 100% | 100% | 100%
| Stepchart | Chanson qui ne marche pas |  | 100% | 100% | 100%
| Wheelsong | Stepchart | Transistion "splashcreen" | 100% | 100% | 100%
300 | MainMenu |  | Ajout 1J, LAN, 8t | 100% | 100% | 100%
| ProfilManager |  | Creation concept | 100% | 100% | 100%
| ProfilManager / Wheelsong |  | Incrustation | 100% | 100% | 100%
| Wheelsong |  | Display medals | 100% | 100% | 100%
| Wheelsong |  | Display best scores | 100% | 100% | 100%
| ScoreScreen |  | Display records | 100% | 100% | 90% | Verifier si la concurrence marche bien (attendre le Online)
400 | ProfilManager / ScoreScreen |  | Incrustation | 100% | 100% | 100%
| SplashScreen | Team Blui |  | 100% | 100% | 100%
| SplashScreen | Init de profile | Retrouver un profil pas save | 100% | 100% | 100%
| SplashScreen | Nouveau profil |  | 100% | 100% | 100%
500 | SplashScreen | Entrée dans le jeu et trans |  | 100% | 100% | 100%
| Asset Graphique | Creation | Fleche | 100% | 100% | 100%
| Asset Graphique | Creation | boule | 100% | 100% | 100%
| Asset Graphique | Creation | Spé | 100% | 100% | 100%
600 | Asset Graphique | Stepchart | Incrustation | 100% | 100% | 100%
| Première phase de test privée |  |  | 100% | 100% | 100%
| Option screen | Creation | Scene | 100% | 100% | 100%
| Option screen | Creation | Default parameters | 100% | 100% | 100%
| Option screen | Creation | Mode "rapide" | 100% | 100% | 100%
| Option screen | Creation | Binding touches | 100% | 100% | 100%
| Option screen | Creation | Profiles | 100% | 100% | 100%
| Option screen | Creation | Audio | 100% | 100% | 100%
| Option screen | Creation | Video | 100% | 100% | 100% | Petit problème avec x8 ?
| Option Screen | Creation | Cache | 100% | 100% | 100%
| General | TO DO |  |  |  |  | son du fail pas assez fort
| General | Incrustation | OptionManager | 100% | 100% | 100%
| WheelSong / Stepchart | Creation | Mode debug offbeat | 100% | 100% | 100%
700 | Mainmenu | OptionScreen | Incrustation | 100% | 100% | 100%
| Stepchart | Mine | Ajouter le son | 100% | 100% | 100%
800 | Wheelsong |  | Tri | 100% | 100% | 100%
| Wheelsong | Rate |  | 100% | 100% | 100%
900 | Cache |  |  | 100% | 100% | 100% | Peut être moyen d'optimiser ? 1750 song = 16 secondes
- | General | Voix |  | 0% | 0% | 0% | Trouver un doubleur
| Stepchart | Modification | Barre de vie à modifier | 100% | 100% | 100%
906 | Stepchart | Modification | Time bar à modifier | 100% | 100% | 100%
| Stepchart | Modification | Background à modifier | 100% | 100% | 100% | Plus tard
1000 | General |  | Correction générale + optim | 100% | 100% | 100%
Première phase de test publique
TOTAL | AVANCEMENT DU PROJET : BUILD 1000 |  | 99.92% | 100% | 100% | 99.77%
|  |  |  | Code | Unity | Test
1100 | Optimisation du code Stepchart |  |  | 100% | 100% | 100%
| Network | Scene | Creation Scene | 100% | 100% | 100%
| Network | GUI | Creation GUI intro | 100% | 100% | 100%
| Network | Creation Network | Création du système | 100% | 100% | 100%
| Network | Scene | Creation scene connexion | 100% | 100% | 100%
| Network | LAN | Echange de profils | 100% | 100% | 100%
| Network | LAN | Verification pack/bind LANManager | 100% | 100% | 100%
| Network | LAN | Creation système connexion | 100% | 100% | 100% | 2013-02-15
| Network | Recupration de profil | Creation | 100% | 100% | 100%
1200 | Wheelsong | GUI | Mise en place du système de distinction GM/others | 0% | 0% | 0%
| Wheelsong | GUI | Mise en place du système de selection global (accepter/refuser) | 0% | 0% | 0%
| Wheelsong | GUI / LAN | Système de chat | 100% | 100% | 100%
| Wheelsong | GUI | Revoir toute l'interface | 100% | 100% | 100%
| Wheelsong | GUI | Lancer la song | 0% | 0% | 0%
1400 | Wheelsong | Test | Testing | 0% | 0% | 0% | 2013-02-28
| Stepchart | LAN | Mise en place RPC partagée | 0% | 0% | 0%
| Stepchart | GUI | Mise en place GUI partagée | 0% | 0% | 0%
1500 | Stepchart | Test | Testing | 0% | 0% | 0% | 2013-03-15
1600 | ScoreScreen | LAN | Ecran de ranking suivant mode | 0% | 0% | 0%
1700 | General | - | Retapage graphique | 0% | 0% | 0%
2000 | MainMenu | LAN | Incrustation | 0% | 0% | 0% | 2013-03-31
| Deuxième phase de test publique |  |  | 0% | 0% | 0%
TOTAL | AVANCEMENT PROJET BUILD 2000 |  | 55% | 55% | 55% | 55%
3000 | Tutorial |  |  | 0% | 0% | 0%
4000 | Modes | Courses |  | 0% | 0% | 0%
| Modes | Survival |  | 0% | 0% | 0%
| Modes | Zone |  | 0% | 0% | 0%
| Stepchart | Mode repeat |  | 0% | 0% | 0%
5000 | Achievements |  |  | 0% | 0% | 0%
6000 | Mode aventure |  |  | 0% | 0% | 0%
v1 | Troisième phase de test |  |  | 0% | 0% | 0%
v1.1 | Mode 8t |  |  | 0% | 0% | 0%
v1.2 | Editor |  |  | 0% | 0% | 0%
Bug | Les mini freeze dans "Guardian mist"
Bug | Refaire la GUI
Bug | Refaire le son
Amélioration | Refaire les graphismes