## Feuil1
prio | next step | next big step | not for now | not decided | En cours de réa
Progression
Stepchart |  |  |  |  | Reste :
| Precision |  |  | 25% | Lien aux arrows, affichage GUI
| Score |  |  | 0% | GUI ? 3DText ? + scoring
| life |  |  | 0% | GUI ? 3D ? + life gestion
| mine |  |  | 0%
| combo |  |  | 0%
| combo-rush |  |  | 0%
| audio |  |  | 0%
| song progressbar |  |  | 0%
| offset |  |  | 0% | A faire rapidement
| background change |  |  | 0%
| Background scene |  |  | 0%
Game screens :
| Score screen |  |  | 0%
| Press start |  |  | 0%
| Mode screen |  |  | 0%
|  | Aventure |  | 0%
|  |  | Normal (1-13) | 0%
|  |  | Expert (9-20) | 0%
|  |  | Super Expert (9-20) | 0%
|  | Fun | 1j, 2j, mode 8t | 0%
|  | Modes |  | 0%
|  |  | Courses random | 0%
|  |  | Survival | 0%
|  |  | Zone | 0%
|  |  | Boss battle | 0%
|  | Option |  | 0%
|  |  | Key mapping | 0%
|  |  | Arrow skin select | 0%
|  |  | timing ? | 0%
|  |  | general offset | 0%
|  |  | graphics options ? | 0%
|  |  | sound option ? | 0%
| Songwheel screen |  |  | 0%
| Song option screen |  |  | 0%
|  | Light options |  | 0%
| Profiles screen |  |  | 0%
|  | Save/Load option |  | 0%
Others stuff
| Achievements |  |  | 0%
| Keyboard/dancepad mode |  |  | 0%
| Font |  |  | 0%
| Asset graphique |  |  | 0%
|  | Medaille |  | 0%
|  | Notes ? Autres ? |  | 0%
Managers
| AventureManager (Stepchart cryptées) |  |  | 0%
| DataManager |  |  | 0%
| SaveManager |  |  | 0%
| TextManager |  |  | 0%
| LoadChartManager |  |  | 0%
|  | Rush/Cross detection |  | 0%